Government of the People's Republic of Bangladesh

Ministry of Planning

Implementation Monitoring & Evaluation Division (IMED)

Sher-e-Banglanagar, Dhaka-1207

Tel: 9110008, Fax: 9180924

E-mail: jsbranch@imed.gov.bd, Website: www.imed.gov.bd

**Request for Expression of Interest (REOI)**

Contract Package No. # Sector-7/SR-

|  |
| --- |
| Government of the people’s Republic of Bangladesh |
| 01 | Ministry/Division:  | [Implementation Monitoring and Evaluation Division](http://www.imed.gov.bd/) |
| 02 | Agency: | [Implementation Monitoring and Evaluation Division](http://www.imed.gov.bd/) |
| 03 | Procuring Entity Name: | [Implementation Monitoring and Evaluation Division](http://www.imed.gov.bd/) |
| 04 | Procuring Entity Code: |  |
| 05 | Procuring Entity District: | Dhaka  |
| 06 | Expression of Interest for Selection of  | Consulting Firm (National).  |
| 07 | EOI Ref No | File No. 21.00.0000.021.02.001.18-80 |
| 08 | Date  | 12/09/2019 |

|  |
| --- |
| Key Information |
| 09 | Procurement Method | Fix Budget  |

|  |
| --- |
| Funding Information |
| 10 | Budget and Source of Funds | Revenue  | Government  |
| 11 | Development Partners  | Not applicable  |

|  |
| --- |
| Particular Information  |
| 12 | Project / Programme Code (if applicable) | Not applicable  |
| 13 | Project / Programme Name (if applicable) | “Construction of residential flats at block-F, Mohammadpur Housing Estate, Mohammadpur, Dhaka (2st Revised”. |
| 14 | EOI Closing Date and Time | Date: 06/10/2019 | Time: 2.00 PM |

|  |
| --- |
| Particular Information  |
| 16 | Brief Description of Assignment  | The specific objectives of the assignment are -16.1 The consultant organization will perform the In-depth Monitoring work according to the TOR determined;16.2 Public Procurement Laws and Rules to be followed in appointing consultant organizations in the In-depth Monitoring;16.4 Review to check whether the activities under the project were conducted in accordance with the approved work plan, DPP or RDPP;16.5 Review and analysis of the project activities to assess whether the objectives of the project could be achieved;16.6 The outcome of the proposed study will show the effectiveness of the project and the recommendation made by the consulting firm would be a guideline to implement similar project in future. |
| 17 | Experience, Resources and Delivery Capacity Required of firm  | (a) At least 1 year of experience must be completed in respect to the relevant assessment of the consulting firm;(b) The maximum age limit for all consultants employed under the consulting firm will be limited to 65 (sixty five);(c) In case of procurement of different products, works and services executed under the project, the relevant laws and regulations (PPA-2006/PPR-2008 and the development partner's guideline, etc.) are relevant and experienced;(d) In-depth Monitoring of this package will be completed in the next maximum 4 months of contract work;(e) Experience in data collection, data processing and preparation of reports from field level; & (f) Sufficient manpower and useful materials/equipments.  |
| 18 | Other Details (if applicable)  |  |
| 19 | Association with foreign firms is  | Not applicable  |
| 20 | Ref No | Phasing of Services  | Location | Indicative Start Date | Indicative Completion Date |
| S1 | Inception report (inclusive of detail work plan, methodology, sample size, strategy etc.) | [Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7 | 15 days after signingthe contract) |  |
| S2 | Submission of 1st draft report including findings with analysis | [Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7 | 75 days after signingthe contract) |  |
| S3 | Submission of 2nd draft report including findings with analysis | [Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7 | 90 days after signingthe contract) |  |
| S4 | Submission of final report (in Bengali and English) | [Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7 | 110 days after signingthe contract) |  |

|  |
| --- |
| Procuring Entity Details  |
| 21 | Name of Official Inviting Expressions of Interest  | Md. Mahmudul Haque |
| 22 | Designation of Official Inviting Expressions of Interest | Joint Secretary (Administration)Implementation Monitoring and Evaluation Division. |
| 23 | Address of Official Inviting Expressions of Interest | Director General [Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7Block-5, Room- 13[Monitoring and Evaluation](http://www.imed.gov.bd/) Sector 7IMED, Ministry of Planning.  |
| 24 | Contact details Official Inviting Expressions of Interest | Tel: 9180606 | Fax.9180749 | E-mail: jsbranch@imed.gov.bd |
| 25 | The procuring entity reserves the right to accept or rejects all EOI’s.  |

**Md. Mahmudul Haque,**

Joint Secretary (Administration)

IMED, Ministry of Planning

Planning Commission Campus,

Sher-e-Bangla Nagar, Dhaka,

e-mail: jsbranch@imed.gov.bd